## SD1
Assessment
Component: | Mobile Technologies
Skills Demo: | 2
Issue Date: | 2019-03-11
Deadline: | 2019-04-01
Project/Skills Demo Plan
Date | Phase | Description
2019-03-11 | Planning | Prepare schedule of various phases of project
2018-03-14 | Design | Design flowchart/sketch/Photoshop mock-up for each activity
2019-03-18 | Implementation | Design and code MainActivity
2019-03-21 | Implementation | Create SQL database and code Second Activity(Database)
2019-03-25 | Implementation | Create API key to access Google Maps service and code Third Activity(Map)
2019-03-27 | Testing | Produce screenshots for each activity including Firebase console(Realtime db), etc
2019-03-30 | Printing | Insert headers/footers/footnotes/screenshots/table of contents/etc as per marking scheme and print
2019-04-01 | Submit | Sign in today or before this date

## SD2
Assessment
Component: | Mobile Technologies
Skills Demo: | 2
Issue Date: | 2019-03-11
Deadline: | 2019-04-01
Project/Skills Demo Plan
Date | Phase | Description
2019-03-11 | Planning | Prepare schedule of various phases of project
2018-03-14 | Design | Design flowchart/sketch/Photoshop mock-up for each activity
2019-03-18 | Implementation | Design and code MainActivity
2019-03-21 | Implementation | Create SQL database and code Second Activity(Database)
2019-03-25 | Implementation | Create API key to access Google Maps service and code Third Activity(Map)
2019-03-27 | Testing | Produce screenshots for each activity including Firebase console(Realtime db), etc
2019-03-30 | Printing | Insert headers/footers/footnotes/screenshots/table of contents/etc as per marking scheme and print
2019-04-01 | Submit | Sign in today or before this date

## SD3
Assessment
Component: | Mobile Technologies
Skills Demo: | 2
Issue Date: | 2019-03-11
Deadline: | 2019-04-01
Project/Skills Demo Plan
Date | Phase | Description
2019-03-11 | Planning | Prepare schedule of various phases of project
2018-03-14 | Design | Design flowchart/sketch/Photoshop mock-up for each activity
2019-03-18 | Implementation | Design and code MainActivity
2019-03-21 | Implementation | Create SQL database and code Second Activity(Database)
2019-03-25 | Implementation | Create API key to access Google Maps service and code Third Activity(Map)
2019-03-27 | Testing | Produce screenshots for each activity including Firebase console(Realtime db), etc
2019-03-30 | Printing | Insert headers/footers/footnotes/screenshots/table of contents/etc as per marking scheme and print
2019-04-01 | Submit | Sign in today or before this date

## OOP
Assessment
Component: | Mobile Technologies
Skills Demo: | 2
Issue Date: | 2019-03-11
Deadline: | 2019-04-01
Project/Skills Demo Plan
Date | Phase | Description
2019-03-11 | Planning | Prepare schedule of various phases of project
2018-03-14 | Design | Design flowchart/sketch/Photoshop mock-up for each activity
2019-03-18 | Implementation | Design and code MainActivity
2019-03-21 | Implementation | Create SQL database and code Second Activity(Database)
2019-03-25 | Implementation | Create API key to access Google Maps service and code Third Activity(Map)
2019-03-27 | Testing | Produce screenshots for each activity including Firebase console(Realtime db), etc
2019-03-30 | Printing | Insert headers/footers/footnotes/screenshots/table of contents/etc as per marking scheme and print
2019-04-01 | Submit | Sign in today or before this date

## Prog
Assessment
Component: | Mobile Technologies
Skills Demo: | 2
Issue Date: | 2019-03-11
Deadline: | 2019-04-01
Project/Skills Demo Plan
Date | Phase | Description
2019-03-11 | Planning | Prepare schedule of various phases of project
2018-03-14 | Design | Design flowchart/sketch/Photoshop mock-up for each activity
2019-03-18 | Implementation | Design and code MainActivity
2019-03-21 | Implementation | Create SQL database and code Second Activity(Database)
2019-03-25 | Implementation | Create API key to access Google Maps service and code Third Activity(Map)
2019-03-27 | Testing | Produce screenshots for each activity including Firebase console(Realtime db), etc
2019-03-30 | Printing | Insert headers/footers/footnotes/screenshots/table of contents/etc as per marking scheme and print
2019-04-01 | Submit | Sign in today or before this date

## Web
Assessment
Component: | Mobile Technologies
Skills Demo: | 2
Issue Date: | 2019-03-11
Deadline: | 2019-04-01
Project/Skills Demo Plan
Date | Phase | Description
2019-03-11 | Planning | Prepare schedule of various phases of project
2018-03-14 | Design | Design flowchart/sketch/Photoshop mock-up for each activity
2019-03-18 | Implementation | Design and code MainActivity
2019-03-21 | Implementation | Create SQL database and code Second Activity(Database)
2019-03-25 | Implementation | Create API key to access Google Maps service and code Third Activity(Map)
2019-03-27 | Testing | Produce screenshots for each activity including Firebase console(Realtime db), etc
2019-03-30 | Printing | Insert headers/footers/footnotes/screenshots/table of contents/etc as per marking scheme and print
2019-04-01 | Submit | Sign in today or before this date